## Sheet1
THREAT ASSESSMENT MATRIX
Probability |  |  |  | Risks
Almost certain / Probability > 80% | 4 |  |  | Low: 1-3
Likely / Probability > 50% - 80% | 3 |  |  | Medium: 4-5
Possible / Probability > 20% - 50% | 2 |  |  | High: 6-8
Unlikely / Probability < 20% | 1
Severity
Severe / Significant increase in budget & completion date | 4
Major / Some increase in budget & completion date | 3
Moderate / Some cost increase, but not to budget. No delay to critical path. | 2
Minor / Minor cost increase, but not to budget. No delay to critical path. | 1
Threat Description | Probability | Severity | P+S | Risk
Extended inclement weather | 2 | 3 | 5 | Medium: 4-5
Flooding | 1 | 2 | 3 | Low: 1-3
Wildfire | 1 | 4 | 5 | Medium: 4-5
Wildlife issues | 1 | 1 | 2 | Low: 1-3
Traffic volumes | 3 | 3 | 6 | High: 6-8
Distracted drivers | 3 | 3 | 6 | High: 6-8
Material procurement delays - contractor furnished | 2 | 2 | 4 | Medium: 4-5
Material procurement delays - town furnished | 2 | 2 | 4 | Medium: 4-5
Lack of labor resources | 2 | 2 | 4 | Medium: 4-5
Lack of equipment resources | 1 | 1 | 2 | Low: 1-3
Not attaining schedule milestones | 2 | 2 | 4 | Medium: 4-5
Not attaining schedule completion date | 1 | 1 | 2 | Low: 1-3
Poor coordination of subcontractor schedules | 2 | 2 | 4 | Medium: 4-5
Not working through issues quickly and efficiently | 1 | 1 | 2 | Low: 1-3
Lack of advance planning | 1 | 3 | 4 | Medium: 4-5
Lack of close coordination | 1 | 1 | 2 | Low: 1-3
Untimely decision making | 2 | 2 | 4 | Medium: 4-5
Untimely response tp RFI's | 1 | 2 | 3 | Low: 1-3
Rework due to lack of timely approvals | 1 | 3 | 4 | Medium: 4-5
Major design changes | 1 | 3 | 4 | Medium: 4-5
Different interpretation of contract requirements | 3 | 1 | 4 | Medium: 4-5
Communication breakdowns | 1 | 4 | 5 | Medium: 4-5
Trust breakdowns | 1 | 4 | 5 | Medium: 4-5
Poor public communications | 1 | 4 | 5 | Medium: 4-5
Potential for differing site conditions | 4 | 4 | 8 | High: 6-8
Unknown utilities | 3 | 4 | 7 | High: 6-8
Utility reolcations delay project work | 4 | 4 | 8 | High: 6-8
Other projects affecting the project schedule | 1 | 1 | 2 | Low: 1-3
Other jurisdictions affecting cost / schedule | 1 | 4 | 5 | Medium: 4-5
Extended business interruptions | 3 | 1 | 4 | Medium: 4-5
Lack of worker housing | 4 | 2 | 6 | High: 6-8